## Sheet1
Work Breakdown Structure
All Works					TODO				Sprint 1

1	Main scene frames				8.1	Additional Features			Day 1			Day 2			Day 3			Day 4			Day 5				Day 6			Day 7
1.1	Draw Mockups				8.1.1	Change Languages					2.1	Background					1.2.6			6.5	Add Score			2.2	Music		5.1	Music volume
1.1.1	Main Menu				8.1.2	Enable Ads					2.1.1	Main menu					6.1	Board setup		6.6	Game end recognization			2.2.1	Main menu		5.1.1	Slider
1.1.2	Settings					2.1.2	Gameplay					6.2	Move mushrooms		6.8	Undo Mechanism			2.2.2	Gameplay		5.1.2	Up/down buttons
1.1.3	Hall of Fame				2.5.2	Mushroom spawn					2.4	Button Theme					6.3	Spawn Mushrooms					2.3	Sfx		5.2	Sfx volume
1.1.4	How to play				2.5.3	Mushroom die					6.4	Destroy Mushrooms					2.3.1	Mouse click/touch		5.2.1	Slider
1.1.5	Credits				2.5.4	Mushroom move					2.3.2	Object picking		5.2.2	Up/down buttons
1.1.6	Gameplay
1.2	Code The Frames				4.1	Casual
1.2.1	Main Menu				4.2	Time Rush			Sprint 2
1.2.2	Settings				4.3	Four Seasons
1.2.3	Hall of Fame				7.2	Set Difficulty (number of unique mushroom colors)			Day 1			Day 2			Day 3			Day 4
1.2.4	How to play				7.3	Custom mushroom			3.1	Save/Load		1.2.3	Hall of Fame		7.1	Set Undo depth		3.2	Connect Google Plays for global players’ high scores
1.2.5	Credits					3.1.1	Game Progress		1.2.4	How to play
1.2.6	Gameplay					3.1.2	User Settings		6.7	Save High Score

2	Animations, Musics & SFX
2.1	Background
2.1.1	Main menu
2.1.2	Gameplay
2.2	Music
2.2.1	Main menu
2.2.2	Gameplay
2.3	Sfx
2.3.1	Mouse click/touch
2.3.2	Object picking

2.4	Button Theme
2.5	Mushroom
2.5.1	Mushroom Artwork
2.5.2	Mushroom spawn
2.5.3	Mushroom die
2.5.4	Mushroom move

3	Features
3.1	Save/Load
3.1.1	Game Progress
3.1.2	User Settings
3.2	Connect Google Plays for global players’ high scores

4	Game Modes
4.1	Casual
4.2	Time Rush
4.3	Four Seasons

5	Settings
5.1	Music volume
5.1.1	Slider
5.1.2	Up/down buttons
5.2	Sfx volume
5.2.1	Slider
5.2.2	Up/down buttons

6	Gameplay
6.1	Board setup
6.2	Move mushrooms
6.3	Spawn Mushrooms
6.4	Destroy Mushrooms
6.5	Add Score
6.6	Game end recognization
6.7	Save High Score

7	Advanced Game Settings
7.1	Set Undo depth
7.2	Set Difficulty (number of unique mushroom colors)
7.3	Custom mushroom

8.1	Additional Features
8.1.1	Change Languages
8.1.2	Enable Ads